## Project Plan
Overall Progress | 48.73% | PHASES | % | STAGES / MODULES | % | ID | ACTIVITIES | STATUS | In-Charge | Date Started | Date Finished | Estimate | Charging | Remarks
|  | Planning | 100% | Meeting with Client | 100% |  | Requirements Gathering | Done | Client | - | - | - | -
Planning Phase | 100% |  |  |  | 100% |  | - Business Requirements | Done | Client | - | - | - | -
Designing Phase | 100% |  |  |  | 100% |  | - User Requirements | Done | Client | - | - | - | -
Development Phase | 46.31% |  |  |  | 100% |  | - Functional Requirements | Done | Client | - | - | - | -
[5 empty] | 100% |  | Requirements Analysis | Done | Client | - | - | - | -
Estimate | 120 Days |  |  |  | 100% |  | Defining of Process | Done | Client | - | - | - | -
[5 empty] | 100% |  | Requirements Review & Approval | Done | Client | - | - | - | -
LEGEND |  | Designing | 100% | Design Planning | 100% |  | Drafting UI Layout | Done | Alvin | - | - | - | -
Charging |  |  |  |  | 100% |  | Designing UI | Done | Alvin, Glenda | - | - | - | - | Sir Jhon & Sir Cezar submitted their Designs
1.0 = 8 hours |  |  |  |  | 100% |  | Designing Final UI Prototype @Figma.com | Done | Alvin | - | - | - | - | Sir Cezar said to stop designing and start coding
0.75 = 6 hours |  |  |  |  | 100% |  | Design Review and Approval | Done | Client | - | - | - | -
0.50 = 4 hours |  | Development Development Development Development Development Development Development Development | 100% | Development Planning | 100% |  | Team Initial Meetings | Done | Alvin, Glenda | Nov-2022 | Dec-2022 | - | -
0.25 = 2 hours |  |  |  |  | 100% |  | Creating Checklist of Project Activities / Project Plan | Done | Alvin | 2023-01-09 | - | - | -
0.125 = 1 hour |  |  |  |  | - |  | Checking/Confirmation of Project Plan by the Team | Pending | Alvin, Glenda | - | - | - | -
|  |  | 100% | Database & Server Module | 100% |  | Git Repository Study (Cloud) | Done | Alvin, Glenda | 2023-01-09 | 2023-01-09 | - | -
Terminologies |  |  |  |  | - |  | Setting up Git Repository | Pending | Glenda
CN = Cloud Navigator |  |  |  |  | - |  | Testing Git Repository | Pending | Alvin, Glenda
[5 empty] | 100% |  | Designing Database | Done | Alvin
Updated: June 8, 2023, 10:07 AM |  |  |  |  | 100% |  | Creating Database | Done | Alvin
[5 empty] | 100% |  | Connecting Database to Client-Side Code | Done | Alvin
|  |  | 50% | User Side UI | 100% |  | Login Page | Done | Glenda | 2022-12-01 | 2022-12-09 |  | 7
[5 empty] | 100% |  | Forgot Password Modal | Done | Glenda | 2023-01-19 | 2023-01-19
Debugging | 0 |  |  |  | - |  | Landing Page | Done | Glenda | 2022-12-12 | 2022-12-23 |  | 10 | Subject for Revision
Pending | 0 |  |  |  | - |  | Home Page | Done | Glenda | 2023-01-03 | 2023-01-16 |  | 10 | Subject for Revision
Fixed | 0 |  |  |  | - |  | Upload Page | Done | Glenda | 2023-01-16 | 2023-01-18 |  |  | Subject for Revision
[5 empty] | - |  | Profile Page | Done | Glenda | 2023-01-16 | 2023-01-18 |  |  | Subject for Revision
Testing |  |  |  |  | - |  | File Tagging Modal | Done | Glenda | 2023-01-18 | 2023-01-24 |  |  | Subject for Revision
Ongoing | 0 |  |  |  | 100% |  | Search / Advance Search UI | Done | Alvin |  |  |  |  | 1
Pending | 0 |  |  |  | 100% |  | File Details Page | Done | Alvin | 2023-04-27 | 2023-04-27 |  | 0.625 | 2
Completed | 0 |  |  |  | 0% |  | Landing Page (REVISED) | Pending | Alvin |  |  | 2
[5 empty] | 50% |  | Home Page (REVISED) | On Hold | Alvin |  |  | 1
[5 empty] | 100% |  | Upload Page (REVISED) | Done | Alvin
[5 empty] | 0% |  | Duplicate Checking Modal | Pending |  |  |  | 0.5
[5 empty] | 100% |  | Profile Page (REVISED) | Done | Alvin
[5 empty] | 100% |  | File Tagging Modal (REVISED) | Done | Alvin |  |  |  | 5
[5 empty] | 100% |  | Photo Tagging Modal (REVISED) | Done | Alvin |  |  |  |  | 1
[5 empty] | - |  | Responsive Web Design (RWD) | - | - | - | - |  | - | -
[5 empty] | 100% |  | - Login Page | Done | Glenda | 2022-12-01 | 2023-01-06 |  | 2
[5 empty] | - |  | - Profile Page | Done | Glenda | 2022-12-16 | 2023-01-18 |  | 2 | Subject for Revision
[5 empty] | - |  | - Upload Page | Done | Glenda | 2023-01-16 | 2023-01-20 |  | 2 | Subject for Revision
[5 empty] | 0% |  | - Profile Page (REVISED) | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | - Upload Page (REVISED) | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | - Landing Page | Pending | Alvin |  |  | 3
[5 empty] | 0% |  | - File Tagging Modal | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | - Visual Tagging Modal | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | - Home Page | Pending | Alvin |  |  | 3
[5 empty] | 0% |  | - File Details Page | Pending | Alvin |  |  | 1
|  |  | 56.92% | Admin Side UI | 100% |  | Dashboard Page | Done | Alvin |  |  |  |  | 5
[5 empty] | - |  | Data Review Page | - | Alvin |  |  | - | - | -
[5 empty] | 100% |  | - For Review | Done | [5 empty] | 1
[5 empty] | 100% |  | - Approved | Done |  |  |  | 1
[5 empty] | 100% |  | - Rejected | Done |  |  |  | 1
[5 empty] | 100% |  | - Cancelled | Done |  |  |  | 1
[5 empty] | 80% |  | Category List Page | Pending | Alvin |  |  | 2
[5 empty] | 80% |  | Tag List Page | Pending | Alvin |  |  | 2
[5 empty] | 80% |  | User List Page | Pending | Alvin |  |  | 2
[5 empty] | - |  | Responsive Web Design (RWD) | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Dashboard Page | Pending | Alvin |  |  | 3
[5 empty] | 0% |  | - Data Review Page | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Category List Page | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Tag List Page | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - User List Page | Pending | Alvin |  |  | 2
|  |  | 0% | Login Page Module | 0% |  | Username Validation | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | Account Checking | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | Forgot Password Feature | Pending | Alvin |  |  | 0.5
|  |  | 0% | Landing Page Module | 0% |  | Login Checker | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | Display Name of Logged User | Pending | Alvin |  |  | 0.0625
[5 empty] | 0% |  | Display Picture of Logged User | Pending | Alvin |  |  | 0.0625
[5 empty] | - |  | Shortcut Filters | - | Alvin |  |  | - | - | -
[5 empty] | 0% |  | - Documents | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | - Photos | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | - Videos | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | - QMS | Pending | Alvin |  |  | 0.5
|  |  | 0% | Profile Page Module | 0% |  | Load User Details | Pending | Alvin |  |  | 0.125
[5 empty] | 0% |  | Load User's Picture | Pending | Alvin |  |  | 0.125
|  |  | 100% | Upload Page Module | - |  | Upload Function | - | - | - | - | - | - | -
[5 empty] | 100% |  | - Open File Dialog Box | Done | Alvin
[5 empty] | 100% |  | - Select Multiple Files | Done | Alvin
[5 empty] | 100% |  | - Save Uploaded Files in Cookies | Done | Alvin | 2023-03-28
[5 empty] | 100% |  | - Insert Data in Database | Done | Alvin
[5 empty] | 100% |  | - Upload Files to Server | Done | Alvin
[5 empty] | 100% |  | Load Uploaded Files in the Table | Done | Alvin
[5 empty] | 100% |  | Hover and Click Row Function | Done | Alvin
[5 empty] | 100% |  | Search in Table Function | Done | Alvin
[5 empty] | 100% |  | Sort Table Column Function | Done | Alvin
[5 empty] | 100% |  | Date Column - Change Format | Done | Alvin
[5 empty] | 100% |  | Delete Uploaded File Function | Done |  | 2023-04-13 | 2023-04-13
[5 empty] | - |  | File Type Filter Function | - | Alvin |  |  | 1 |  | Study - DataTables Filters
[5 empty] | - |  | Status Filter Function | - | Alvin |  |  | 1 |  | Study - DataTables Filters
|  |  | 0% | Duplicate Checking Module | 0% |  | Duplicate Checking Function | Pending
[5 empty] | 0% |  | Show "N number of Duplicates Found" Warning | Pending
[5 empty] | 0% |  | Show Duplicate Checking Modal if necessary | Pending
[5 empty] | - |  | Load Duplicates from New Upload | - |  | - | - | - | - | -
[5 empty] | 0% |  | - Collect Data from New Uploads | Pending
[5 empty] | 0% |  | - Load corresponding Picture | Pending
[5 empty] | 0% |  | - Next/Prev Button Functionality | Pending
[5 empty] | 0% |  | - Load Counter | Pending
[5 empty] | 0% |  | - Load File Name | Pending
[5 empty] | 0% |  | - Load File Size | Pending
[5 empty] | 0% |  | - "Keep" Button Functionality | Pending
[5 empty] | 0% |  | - "Delete" Button Functionality | Pending
[5 empty] | - |  | Load Duplicates from Database | - |  | - | - | - | - | -
[5 empty] | 0% |  | - Collect Data from Database | Pending
[5 empty] | 0% |  | - Load corresponding Picture | Pending
[5 empty] | 0% |  | - Next/Prev Button Functionality | Pending
[5 empty] | 0% |  | - Load Counter | Pending
[5 empty] | 0% |  | - Load File Name | Pending
[5 empty] | 0% |  | - Load Raw Name | Pending
[5 empty] | 0% |  | - Load File Size | Pending
[5 empty] | 0% |  | - Load Uploader | Pending
[5 empty] | 0% |  | - Load Date Uploaded | Pending
[5 empty] | 0% |  | File Size Converter - Byte to MB | Pending
[5 empty] | 0% |  | Delete Duplicate Uploads if Modal was Closed | Pending
|  |  | 88.24% | File Tagging Module | 100% |  | Show File Tagging Modal | Done | Alvin
[5 empty] | 100% |  | Load File Name | Done | Alvin
[5 empty] | 100% |  | Load Recently Uploaded Files to Modal | Done | Alvin | 2023-04-03 | 2023-04-03 |  |  | 0.5
[5 empty] | 100% |  | Load All "Waiting to Tag" Files to Modal | Done |  | 2023-04-03 | 2023-04-03 |  |  | 0.5
[5 empty] | 100% |  | File Type Checker Function | Done | Alvin | 2023-04-14 | 2023-04-14 |  |  | 0.25
[5 empty] | 100% |  | Load File Type Logo | Done | Alvin | 2023-04-17 | 2023-04-17 |  | 0.125 | 0.125
[5 empty] | 100% |  | Uploaded Files Counter Function | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | Next/Prev of Uploaded Files Function | Done | Alvin | 2023-04-03 | 2023-04-03 |  |  | 0.5
[5 empty] | 0% |  | Load Designated Group | Pending | Alvin |  |  | 0.0625
[5 empty] | 100% |  | Load Categories | Done | Alvin
[5 empty] | 100% |  | Add Custom Categories Function | Done | Alvin
[5 empty] | 100% |  | Remove Added Custom Categories Function | Done | Alvin
[5 empty] | 100% |  | Add Custom Tags Function | Done | Alvin
[5 empty] | 100% |  | Remove Added Custom Tags Function | Done | Alvin
[5 empty] | 100% |  | Visual Tagging Switcher Function | Done | Alvin
[5 empty] | 0% |  | Clear Inputs Function | Pending | Alvin |  |  | 0.125
[5 empty] | 100% |  | Save to Review Function | Done | Alvin | 2023-04-11 | 2023-04-11 |  | 1 | 1
|  |  | 54.55% | Photo Tagging Module | 100% |  | Show Visual Tagging Modal | Done | Alvin
[5 empty] | 100% |  | Load File Name | Done | Alvin
[5 empty] | 100% |  | Load Uploaded Files | Done | Alvin |  |  |  |  | 1
[5 empty] | 100% |  | Uploaded Files Counter Function | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | Next/Prev of Uploaded Files Function | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 0% |  | Load Designated Group | Pending | Alvin |  |  | 0.0625 |  | 0.0625
[5 empty] | 100% |  | Load Plant Types | Done | Alvin |  |  |  |  | 0.125
[5 empty] | 100% |  | Load Project Name | Done | Alvin |  |  |  |  | 0.125
[5 empty] | 100% |  | Remove Added Custom Categories Function | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 100% |  | Add Custom Tags Function | Done | [5 empty] | 0.25
[5 empty] | - |  | Adding Custom Visual Tags | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Click Picture to Add Custom Tag | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Get Coordinates Function | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | - Show Dropdown List of Tags | Pending | Alvin |  |  | 3
[5 empty] | 0% |  | - Search Function in Dropdown List | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Type and Add Custom Tag Function | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Show Added Visual Tag in Picture | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Show Added Visual Tag in Tagging Section | Pending | Alvin |  |  | 2
[5 empty] | 100% |  | Remove Added Custom Tags Function | Done | Alvin |  |  |  |  | 1
[5 empty] | 100% |  | File Tagging Switcher Function | Done | Alvin
[5 empty] | 0% |  | Clear Inputs Function | Pending | Alvin |  |  | 1
[5 empty] | - |  | Apply to All Function | - |  | - | - | - | - | Not Needed
[5 empty] | 100% |  | Save to Review Function | Done | [5 empty] | 1
[5 empty] | 0% |  | Modal Confirmation UI | Pending | Alvin |  |  | 0.5
|  |  | 60% | Home Page: Advance Search Module | 100% |  | Show "Advance Search Box" when Typing in "Search Input" | Done | Alvin |  |  |  |  | 2
[5 empty] | 100% |  | Clear Input Search Function | Done | Alvin |  |  |  |  | 2
[5 empty] | - |  | Suggested Words Section | - | - | - | - | - | - | -
[5 empty] | 100% |  | - Show Suggested Words | Done | Alvin |  |  |  |  | 3
[5 empty] | 100% |  | - Sort Alphabetically | Done | [5 empty] | 0.125
[5 empty] | 0% |  | - Add Function on each Words to Advance Search Section | Pending | Alvin |  |  | 2
[5 empty] | - |  | Advance Search Section | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Show Advance Search Section | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Remove Function on each added Word | Pending | Alvin |  |  | 1
[5 empty] | 100% |  | Update Main Contents based on Search Input | Done | Alvin |  |  |  |  | 2
[5 empty] | 100% |  | Add Searched Word in "Search Results for..." when hit enter | Done | Alvin |  |  |  |  | 0.25
[5 empty] | 0% |  | Hide "Advance Search Box" when hit enter | Pending | Alvin |  |  | 0.25
|  |  | 54.17% | Home Page: Search Filter Module | - |  | File Types Section | - | - | - | - | - | - | -
[5 empty] | 100% |  | - Load "All" File Types Counter | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | - Load "Documents" File Counter | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | - Load "Photos" File Counter | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | - Load "Videos" File Counter | Done | Alvin
[5 empty] | 100% |  | - Load "Others" File Counter | Done | Alvin
[5 empty] | - |  | 'Others' Section | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Load "QMS" File Counter | Pending | Alvin |  |  | 0.0625
[5 empty] | 0% |  | - Load "3D Models" File Counter | Pending | Alvin |  |  | 0.0625
[5 empty] | 0% |  | - Load "Drawings" File Counter | Pending | Alvin |  |  | 0.0625
[5 empty] | - |  | Business Units Section | - | - | - | - | - | - | -
[5 empty] | 100% |  | - Load Business Units | Done | [5 empty] | 1
[5 empty] | 100% |  | - Load Counter on each Business Units | Done | Alvin |  |  |  |  | 0.25
[5 empty] | 100% |  | - Show only BU with files uploaded | Done | [5 empty] | 1
[5 empty] | - |  | Categories | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Load all Custom Categories | Pending |  |  |  | 0.5
[5 empty] | 100% |  | - Load all "Plant Types" (for EE) | Done | [5 empty] | 1
[5 empty] | 100% |  | - Load all "Project Names" (for EE) | Done | [5 empty] | 1
[5 empty] | 0% |  | - Load Counter on each Category | Pending | Alvin |  |  | 0.25
[5 empty] | 100% |  | - Load Counter on each "Plant Type" (for EE) | Done | Alvin |  |  |  |  | 0.25
[5 empty] | 100% |  | - Load Counter on each "Project Name" (for EE) | Done | Alvin |  |  |  |  | 0.25
[5 empty] | 0% |  | "Clear Filters" Function | Pending | Alvin |  |  | 1
[5 empty] | - |  | Update Main Contents when Checkboxes is Ticked | - |  | - | - | - | - | -
[5 empty] | 100% |  | - File Types Section | Done | [5 empty] | 1
[5 empty] | 0% |  | - Others Section | Pending |  |  |  | 1
[5 empty] | 0% |  | - Business Units Section | Pending |  |  |  | 1
[5 empty] | 0% |  | - Categories: Plant Type | Pending |  |  |  | 1
[5 empty] | 0% |  | - Categories: Project Name | Pending |  |  |  | 1
[5 empty] | 0% |  | - Categories: Custom | Pending | Alvin |  |  | 1
|  |  | 50% | Home Page: Main Contents | 100% |  | Show "Search Results for..." when hit enter in Search Input | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 0% |  | "Sort by" Functionality (Latest, Oldest, A-Z, Z-A) | Pending | Alvin |  |  | 1
[5 empty] | 100% |  | Load Documents Section (Default) | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 100% |  | Load Photos Section (Default) | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 100% |  | Load Videos Section (Default) | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 0% |  | Load QMS Section (Default) | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | Load 3D Models Section (Default) | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | Load Drawings Section (Default) | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | Hide Section if has no Items to Show | Pending | Alvin |  |  | 0.5
[5 empty] | 100% |  | Link "File Details Page" on each Items | Done | Alvin |  |  |  |  | 0.5
|  |  | 27.27% | File Details Page | 100% |  | Check URL and Display its Data | Done | Alvin |  |  | 2
[5 empty] | 0% |  | Load Breadcrumbs (Item Navigation Path) | Pending | Alvin |  |  | 1
[5 empty] | 100% |  | Load Item Name | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | Load Item Categories | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 100% |  | Load Item Tags | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 0% |  | Load Item Description | Pending | Alvin |  |  | 0.125
[5 empty] | 0% |  | Load Item Section Result Counter | Pending | Alvin |  |  | 0.25
[5 empty] | 100% |  | Load Item Remarks | Done | Alvin |  |  |  |  | 0.5
[5 empty] | 0% |  | Breadcrumbs Function | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | Carousel Button Function | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | Categories Link Function | Pending | Alvin |  |  | 1
[5 empty] | 100% |  | Download Button Function | Done | Alvin |  |  |  |  | 1
[5 empty] | - |  | Documents (Word, Excel, PPT) | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Load Document Name | Pending | Alvin |  |  | 0.125
[5 empty] | 0% |  | - Load Document Logo | Pending | Alvin |  |  | 0.5
[5 empty] | - |  | PDF | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Load PDF Preview using iFrame | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | - Open in New Tab Button Function | Pending | Alvin |  |  | 0.5
[5 empty] | - |  | Photos | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Load Initial Visual Tags | Pending | Alvin |  |  | 5
[5 empty] | 0% |  | - Toggle Initial Tags | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Toggle Tags Function | Pending | Alvin |  |  | 2
[5 empty] | 0% |  | - Maximize Button Function | Pending | Alvin |  |  | 2
[5 empty] | - |  | Videos | - | - | - | - | - | - | -
[5 empty] | 0% |  | - Load Video | Pending | Alvin |  |  | 0.5
[5 empty] | 0% |  | - Video Controls Function | Pending | Alvin |  |  | 0.25
|  |  | 100% | Admin Page Template | 100% |  | Load Header | Done | Alvin |  |  |  |  | 1
[5 empty] | 100% |  | Load Navigation Side Panel | Done | Alvin |  |  |  |  | 1
[5 empty] | 100% |  | Load Default Page | Done | Alvin |  |  |  |  | 1
|  |  | 50% | Admin: Dashboard | 100% |  | Load Page Title | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | Load Pending, Approved, Rejected Card | Done | Alvin |  |  |  |  | 2
[5 empty] | 0% |  | Load Categories and Tags Pie Chart | Pending | Alvin |  |  | 5
[5 empty] | 100% |  | Pending Counter Function | Done | Alvin |  |  |  |  | 0.125
[5 empty] | 100% |  | Approved Counter Function | Done | Alvin |  |  |  |  | 0.125
[5 empty] | 100% |  | Rejected Counter Function | Done | Alvin |  |  |  |  | 0.125
[5 empty] | 0% |  | Categories Counter Function | Pending | Alvin |  |  | 0.125
[5 empty] | 0% |  | Tags Counter Function | Pending | Alvin |  |  | 0.125
[5 empty] | 0% |  | Pie Chart Categories Function | Pending | Alvin |  |  | 5
[5 empty] | 0% |  | Pie Chart Tags Function | Pending | Alvin |  |  | 5
|  |  | 45% | Admin: Data Review | 100% |  | Load Page Title | Done | Alvin |  |  |  |  | 0.0625
[5 empty] | 100% |  | Load Default Table View | Done | Alvin |  |  |  |  | 1
[5 empty] | 0% |  | Status Filter Function | Pending | Alvin |  |  | 2
[5 empty] | 100% |  | Search in Table Function | Done | Alvin |  |  |  |  | 1
[5 empty] | 0% |  | Status Color Coding Function | Pending | Alvin |  |  | 1
[5 empty] | 0% |  | Row Click to Show Modal Function | Pending |  |  |  | 0.25
[5 empty] | 0% |  | Modal - Update Function | Pending |  |  |  | 1
[5 empty] | - |  | Pending | - |  |  |  | - | - | -
[5 empty] | 100% |  | - Load "Pending" Table | Done | [5 empty] | 0.5
[5 empty] | 100% |  | - Search in Table Function | Done | [5 empty] | 0.25
[5 empty] | 0% |  | - Row Click to Show Modal Function | Pending |  |  |  | 0.25
[5 empty] | 0% |  | - Modal - Load Item Details Function | Pending
[5 empty] | 0% |  | - Modal - Update Pending Item Function | Pending |  |  |  | 1
[5 empty] | - |  | Approved | - |  |  |  | - | - | -
[5 empty] | 100% |  | - Load "Approved" Table | Done | [5 empty] | 0.5
[5 empty] | 100% |  | - Search in Table Function | Done | [5 empty] | 0.25
[5 empty] | 0% |  | - Row Click to Show Modal Function | Pending |  |  |  | 0.25
[5 empty] | 0% |  | - Modal - Update Approved Item Function | Pending |  |  |  | 1
[5 empty] | - |  | Rejected | - |  |  |  | - | - | -
[5 empty] | 100% |  | - Load "Rejected" Table | Done | [5 empty] | 0.5
[5 empty] | 100% |  | - Search in Table Function | Done | [5 empty] | 0.25
[5 empty] | 0% |  | - Row Click to Show Modal Function | Pending |  |  |  | 0.25
[5 empty] | 0% |  | - Modal - Update Rejected Item Function | Pending |  |  |  | 1
|  |  | 0% | Admin: Categories | 0% |  | Load "Categories" Table | Pending |  |  |  | 0.5
[5 empty] | 0% |  | Search in Table Function | Pending |  |  |  | 0.25
[5 empty] | 0% |  | Load Add Category Modal | Pending |  |  |  | 0.25
[5 empty] | 0% |  | Update Item Category Function | Pending |  |  |  | 0.5
|  |  | 0% | Admin: Tags | 0% |  | Load "Tags" Table | Pending |  |  |  | 0.5
[5 empty] | 0% |  | Search in Table Function | Pending |  |  |  | 0.25
[5 empty] | 0% |  | Load Add Tag Modal | Pending |  |  |  | 0.25
[5 empty] | 0% |  | Update Item Tag Function | Pending |  |  |  | 0.5
|  |  | 0% | Admin: User List | 0% |  | Load "User List" Table | Pending |  |  |  | 1
[5 empty] | 0% |  | Search in Table Function | Pending |  |  |  | 0.25
[5 empty] | 0% |  | Load Update Access Modal | Pending |  |  |  | 0.5
[5 empty] | 0% |  | Update User Access Function | Pending |  |  |  | 0.5

## Debugging
Ticket | Item ID | Description | Status | Remarks | Date Reported | Date Started | Date Finished | Debugged by
Bug-0001

## Testing
Ticket | Item ID | Description | Status | Remarks | Date Started | Date Finished | Tested by
Test-0001
Test-0002

## Conversation
ID | Description | Date | Status | Remarks | Said/Requested by
C001 | File Tagging: Remove Custom Categories, Add Project Name & Plant Type Selection | 2023-04-03 | Done | Add "Not Applicable" | Sir Jhon Godoy
C002 | File Tagging: Make "Create New File Name" OPTIONAL | 2023-04-03 | Done | Lessen hassle on thinking new file names. | Sir Jhon Godoy
C003 | Uploading: Delete Duplicates if modal was closed | 2023-05-08 | Pending |  | Sir Jhon Godoy

## Reports
Overall Progress | 48.73%
Planning Phase | 100%
Designing Phase | 100%
Development Phase | 46.31%
Estimate | 120 Days
|  |  | Development Phase Modules | % | Status
|  | 1 | Admin Page Template | 100% | Done
|  | 2 | Database & Server Module | 100% | Done
|  | 3 | Development Planning | 100% | Done
|  | 4 | Upload Page Module | 100% | Done
|  | 5 | File Tagging Module | 88.24%
|  | 6 | Home Page: Advance Search Module | 60%
|  | 7 | Admin Side UI | 56.92%
|  | 8 | Photo Tagging Module | 54.55%
|  | 9 | Home Page: Search Filter Module | 54.17% | Ongoing
|  | 10 | Admin: Dashboard | 50%
|  | 11 | Home Page: Main Contents | 50%
|  | 12 | User Side UI | 50%
|  | 13 | Admin: Data Review | 45%
|  | 14 | File Details Page | 27.27%
|  | 15 | Admin: Categories | 0%
|  | 16 | Admin: Tags | 0%
|  | 17 | Admin: User List | 0%
|  | 18 | Duplicate Checking Module | 0%
|  | 19 | Landing Page Module | 0%
|  | 20 | Login Page Module | 0%
|  | 21 | Profile Page Module | 0%